## Unit Test
Unit-Test TestCases for IoTMS
| TC ID | Category | Pacakge | Function | Input | Input Value | Expected Result | Result | Pass/Fail | Test Owner | Description
| TC_RM_001 | Unit | RuleManager | createRule | Rule := Actions + Conditions | rule string | 1. Rule is added if no conflict 2. Return error if conflict | 1. Rule is added if no conflict 2. Return error if conflict | Pass | Bohyun Jung | Create a rule (do actions in condition) 1. Check validity with exist rule in ruleset. (same rule, and conflict rule) 2. Return false if new rule is not valid on 1. 3. If it is new rule, create rule. 4. If there are ruls on same condition, add new actions on exist rule. 5. Update ruleset based on 3~4
| TC_RM_002 | Unit | RuleManager | searchRule | Node ID | N/A or nodeID | 1. send searched rules to UI via EventBus. | 1. send searched rules to UI via EventBus. | Pass | Bohyun Jung | 1. Search rules on specified condition and return matched rule. 2. Return whole rules if condition does not specified.
| TC_RM_003 | Unit | RuleManager | deleteRule | Rule := Actions + Conditions | rule string | 1. Rule is deleted if exist. | 1. Rule is deleted if exist. | Pass | Bohyun Jung | 1. Search rule on givin condition. 2. delete actions if there are some actions left on same condition. 3. delete rule if there is no action left on same condition
| TC_RM_004 | Unit | RuleManager | changeMode | mode (alarm, normal) | mode string | 1. mode changed. 2. rule is activate/inactivated based on mode | 1. mode changed. 2. rule is activate/inactivated based on mode | Pass | Bohyun Jung | 1. Do actions if exist based on rule. (ex. Close door before set alarm) 2. cancle sheduled actions if exist. (ex. If alarm unset, delete scheduled alarm set action) 3. activate/deactivate rules based on the mode.
| TC_RM_005 | Unit | RuleManager | do_action | Action | action string | 1. send actions event to NodeManager via EventBus 2. Ignore actions if it is prohivited with rule | 1. send actions event to NodeManager via EventBus 2. Ignore actions if it is prohivited with rule | Pass | Bohyun Jung | 1. Search action list on current condition (mode) 2. check action is on not allowed list. (ex. Do not open in alarm mode) 3. execute action if it is not blocked on rule.
| TC_RM_006 | Unit | RuleManager | do_thingEvent | Actuator change event | thing string | 1. If the thing event is defined on ruleset, then send actions event to NodeManager via EventBus 2. Do nothing if there is no rule on the even.t | 1. If the thing event is defined on ruleset, then send actions event to NodeManager via EventBus 2. Do nothing if there is no rule on the even.t | Pass | Bohyun Jung | 1. Search ruleset if the thing event matches conditions. 2. If matches, execute actions. 3. If matched actions is delay actions, put it to scheduler (such as turn off light after 10 mins)
| TC_RM_007 | Unit | RuleManager | changeConfig | configuration | time | 1. configuration value is changed . 2. DB is updated. 3. Delay action is updated. | 1. configuration value is changed . 2. DB is updated. 3. Delay action is updated. | Pass | Bohyun Jung | 1. Get config value from UI. 2. Update config value to DB. 3. update delay time on delay action.
| TC_RM_008 | Unit | RuleManager | updateNode | Node connection information | node ID, " Conn" / "DisConn" | 1. activate/inactivate rule on the node | 1. activate/inactivate rule on the node | Pass | Bohyun Jung | 1. If node is disconnected, inactivate rules on the node. 2. If node is connected, activate rules on the node.
| TC_NM_001 | Unit | NodeManager | doCommand | Action Command from RuleManager | "NodeID" ,"12:23:34:45:56:67" "ThingID", {0001~0009} "Value", {Open/Close}, {On/Off}, {AtHome/Away}, {number}, {number}, {Open/Close}, {Empty/Mail}, {Set/Unset}, {number} | 1. Send action command to Link | 1. Send action command to Link | Pass | Dongog Min
| TC_NM_002 | Unit | NodeManager | showNodeInfo | Request NodeInfo from UI | "NodeID" ,"12:23:34:45:56:67" | 1. Update current stroed things information to UI | 1. Update current stroed things information to UI | Pass | Dongog Min
| TC_NM_003 | Unit | NodeManager | showThingInfo | Request ThingInfo from UI | "NodeID" ,"12:23:34:45:56:67" "ThingID", {0001~0009} | 1. Update current stroed thing information to UI | 1. Update current stroed thing information to UI | Pass | Dongog Min
| TC_NM_004 | Unit | NodeManager | registerNode | Request to registerNode from UI | "NodeID" ,"12:23:34:45:56:67" "URL", "lgteam2.cc.cmu.edu" "Port", "550" "SerialNumber", "12345678" | 1. Send request register to Discover | 1. Send request register to Discover | Pass | Dongog Min
| TC_NM_005 | Unit | NodeManager | discoverNode | Request to discoverNode from UI | None | 1. Send request discover to Discover | 1. Send request discover to Discover | Pass | Dongog Min
| TC_NM_006 | Unit | NodeManager | updateThingInfo | Updated things information from SA node | "ThingID", {0001~0009} "Type", {"Door", "Light", "Presense", "Temperature", "Humidity", DoorSensor", "MailBox", "Alarm", etc} "Value", {Open/Close}, {On/Off}, {AtHome/Away}, {number}, {number}, {Open/Close}, {Empty/Mail}, {Set/Unset}, {number} | 1. Update changed information to RuleManager and UI | 1. Update changed information to RuleManager and UI | Pass | Dongog Min
| TC_NM_007 | Unit | NodeManager | removeNode | Request removeNode from UI | "NodeID" ,"12:23:34:45:56:67" | 1. Remove node and node's information | 1. Remove node and node's information | Pass | Dongog Min
| TC_SA_001 | Unit | SA Node (Arduino) | SendJSONobject | JSON object : key , value | "NodeID" , "12:23:34:45:56:67" | Send JSON object(below) to WiFi "NodeID":"12:23:34:45:56:67" | Send JSON object(below) to WiFi "NodeID":"12:23:34:45:56:67" | Pass | JW Hyun | 1. Generate JSON object with key and value. 2. Convert JSON obect to String 3. Send String to WiFi
| TC_SA_002 | Unit | SA Node (Arduino) | SendJSONdiscover | discover JSON message - Job - NodeID - ThingList : ID,Type, Stype, Vtype,Vmin, VMax | Job = "Discovered" NodeID = "12:23:34:45:56:67" ThingList = "0001","Door" ,"Actuator","String","Open" ,"Close" "0002","Light" ,"Actuator","String","On" ,"Off" "0003","Presence" ,"Sensor" ,"String","AtHome","Away" "0004","Temperature","Sensor" ,"Number","-50" ,"50" "0005","Humidity" ,"Sensor" ,"Number","0" ,"100" "0006","DoorSensor" ,"Sensor" ,"String","Open" ,"Close" "0007","MailBox" ,"Sensor" ,"String","Empty" ,"Mail" "0008","Alarm" ,"Actuator","String","Set" ,"Unset" | Send discover JSON message(below) to WiFi { "Job" : "Discovered", "NodeID" : "12:23:34:45:56:67", "ThingList" : [ {"Id":"0001","Type":"Door" ,"SType":"Actuator","VType": "String","VMin" : "Open" ,"VMax" : "Close"}, {"Id":"0002","Type":"Light" ,"SType":"Actuator","VType": "String","VMin" : "On" ,"VMax" : "Off" }, {"Id":"0003","Type":"Presence" ,"SType":"Sensor" ,"VType": "String","VMin" : "AtHome","VMax" : "Away" }, {"Id":"0004","Type":"Temperature","SType":"Sensor" ,"VType": "Number","VMin" : "-50" ,"VMax" : "50" }, {"Id":"0005","Type":"Humidity" ,"SType":"Sensor" ,"VType": "Number","VMin" : "0" ,"VMax" : "100" }, {"Id":"0006","Type":"DoorSensor" ,"SType":"Sensor" ,"VType": "String","VMin" : "Open" ,"VMax" : "Close"}, {"Id":"0007","Type":"MailBox" ,"SType":"Sensor" ,"VType": "String","VMin" : "Empty" ,"VMax" : "Mail" }, {"Id":"0008","Type":"Alarm" ,"SType":"Actuator","VType": "String","VMin" : "Set" ,"VMax" : "Unset"} ] } | Send discover JSON message(below) to WiFi { "Job" : "Discovered", "NodeID" : "12:23:34:45:56:67", "ThingList" : [ {"Id":"0001","Type":"Door" ,"SType":"Actuator","VType": "String","VMin" : "Open" ,"VMax" : "Close"}, {"Id":"0002","Type":"Light" ,"SType":"Actuator","VType": "String","VMin" : "On" ,"VMax" : "Off" }, {"Id":"0003","Type":"Presence" ,"SType":"Sensor" ,"VType": "String","VMin" : "AtHome","VMax" : "Away" }, {"Id":"0004","Type":"Temperature","SType":"Sensor" ,"VType": "Number","VMin" : "-50" ,"VMax" : "50" }, {"Id":"0005","Type":"Humidity" ,"SType":"Sensor" ,"VType": "Number","VMin" : "0" ,"VMax" : "100" }, {"Id":"0006","Type":"DoorSensor" ,"SType":"Sensor" ,"VType": "String","VMin" : "Open" ,"VMax" : "Close"}, {"Id":"0007","Type":"MailBox" ,"SType":"Sensor" ,"VType": "String","VMin" : "Empty" ,"VMax" : "Mail" }, {"Id":"0008","Type":"Alarm" ,"SType":"Actuator","VType": "String","VMin" : "Set" ,"VMax" : "Unset"} ] } | Pass | JW Hyun | 1. Generate JSON message using things information 2. Convert JSON message to String 3. Send String to WiFi
| TC_SA_003 | Unit | SA Node (Arduino) | SendJSONRegister | registered JSON message - Job - NodeID - Result - ThingList : ID,Type, Stype, Vtype,Vmin, VMax | Job = "Registered" NodeID = "12:23:34:45:56:67" Result = "Authorized" ThingList = "0001","Door" ,"Actuator","String","Open" ,"Close" "0002","Light" ,"Actuator","String","On" ,"Off" "0003","Presence" ,"Sensor" ,"String","AtHome","Away" "0004","Temperature","Sensor" ,"Number","-50" ,"50" "0005","Humidity" ,"Sensor" ,"Number","0" ,"100" "0006","DoorSensor" ,"Sensor" ,"String","Open" ,"Close" "0007","MailBox" ,"Sensor" ,"String","Empty" ,"Mail" "0008","Alarm" ,"Actuator","String","Set" ,"Unset" | Send registered JSON message(below) to WiFi { "Job" : "Registered", "NodeID" : "12:23:34:45:56:67", "Result" : "Authorized", "ThingList" : [ {"Id":"0001","Type":"Door" ,"SType":"Actuator","VType": "String","VMin" : "Open" ,"VMax" : "Close"}, {"Id":"0002","Type":"Light" ,"SType":"Actuator","VType": "String","VMin" : "On" ,"VMax" : "Off" }, {"Id":"0003","Type":"Presence" ,"SType":"Sensor" ,"VType": "String","VMin" : "AtHome","VMax" : "Away" }, {"Id":"0004","Type":"Temperature","SType":"Sensor" ,"VType": "Number","VMin" : "-50" ,"VMax" : "50" }, {"Id":"0005","Type":"Humidity" ,"SType":"Sensor" ,"VType": "Number","VMin" : "0" ,"VMax" : "100" }, {"Id":"0006","Type":"DoorSensor" ,"SType":"Sensor" ,"VType": "String","VMin" : "Open" ,"VMax" : "Close"}, {"Id":"0007","Type":"MailBox" ,"SType":"Sensor" ,"VType": "String","VMin" : "Empty" ,"VMax" : "Mail" }, {"Id":"0008","Type":"Alarm" ,"SType":"Actuator","VType": "String","VMin" : "Set" ,"VMax" : "Unset"} ] } | Send registered JSON message(below) to WiFi { "Job" : "Registered", "NodeID" : "12:23:34:45:56:67", "Result" : "Authorized", "ThingList" : [ {"Id":"0001","Type":"Door" ,"SType":"Actuator","VType": "String","VMin" : "Open" ,"VMax" : "Close"}, {"Id":"0002","Type":"Light" ,"SType":"Actuator","VType": "String","VMin" : "On" ,"VMax" : "Off" }, {"Id":"0003","Type":"Presence" ,"SType":"Sensor" ,"VType": "String","VMin" : "AtHome","VMax" : "Away" }, {"Id":"0004","Type":"Temperature","SType":"Sensor" ,"VType": "Number","VMin" : "-50" ,"VMax" : "50" }, {"Id":"0005","Type":"Humidity" ,"SType":"Sensor" ,"VType": "Number","VMin" : "0" ,"VMax" : "100" }, {"Id":"0006","Type":"DoorSensor" ,"SType":"Sensor" ,"VType": "String","VMin" : "Open" ,"VMax" : "Close"}, {"Id":"0007","Type":"MailBox" ,"SType":"Sensor" ,"VType": "String","VMin" : "Empty" ,"VMax" : "Mail" }, {"Id":"0008","Type":"Alarm" ,"SType":"Actuator","VType": "String","VMin" : "Set" ,"VMax" : "Unset"} ] } | Pass | JW Hyun | 1. Generate JSON message using things information 2. Convert JSON message to String 3. Send String to WiFi
| TC_SA_004 | Unit | SA Node (Arduino) | SendJSONstatusEvent | current sensor value JSON message - Job - NodeID - Status : ID,Type, Value | Job = "Registered" NodeID = "12:23:34:45:56:67" Status = "0003","Presence" ,"Away" "0004","Temperature","-999" "0005","Humidity" ,"100" "0006","DoorSensor" ,"Close" "0007","MailBox" ,"Mail" | Send current sensor value JSON message(below) to WiFi { "Job" : "Registered", "NodeID" : "12:23:34:45:56:67", "Status" : [ {"Id":"0003","Type":"Presence" ,"Value":"Away"}, {"Id":"0004","Type":"Temperature","Value":"-999"}, {"Id":"0005","Type":"Humidity" ,"Value":"100"}, {"Id":"0006","Type":"DoorSensor" ,"Value":"Close"}, {"Id":"0007","Type":"MailBox" ,"Value":"Mail"} ] } | Send current sensor value JSON message(below) to WiFi { "Job" : "Registered", "NodeID" : "12:23:34:45:56:67", "Status" : [ {"Id":"0003","Type":"Presence" ,"Value":"Away"}, {"Id":"0004","Type":"Temperature","Value":"-999"}, {"Id":"0005","Type":"Humidity" ,"Value":"100"}, {"Id":"0006","Type":"DoorSensor" ,"Value":"Close"}, {"Id":"0007","Type":"MailBox" ,"Value":"Mail"} ] } | Pass | JW Hyun | 1. Generate JSON message using current sensor value 2. Convert JSON message to String 3. Send String to WiFi
Note on G2: dongog.min: Value or Set of value

## Integration Test
Integration-Test TestCases for IoTMS
| TC ID | Category | Pacakge | Function | Input | Input Value | Expected Result | Result | Pass/Fail | Test Owner | Description
| TC_CM_SA_01 | Integration | Node Manager Comm Manager Arduino (SA Node) | Discover Node | Discover Msg | {"Job":"Discover","Duration":"20","Targets":["NodeManager"]} | Discovered Node Info {"Job":"Discovered","NodeID":"12:23:34:45:56:67","ThingList":[{"Id":"0001","Type":"Door","SType":"Actuator","VType":"String""VMin":"Open""VMax":"Close"},{"Id":"0002","Type":"Light","SType":"Actuator","VType":"String""VMin":"On""VMax":"Off"},{"Id":"0003","Type":"Presence","SType":"Sensor","VType":"String""VMin":"AtHome""VMax":"Away"},{"Id":"0004","Type":"Temperature","SType":"Sensor","VType":"Number""VMin":"-50""VMax":"50"},{"Id":"0005","Type":"Humidity","SType":"Sensor","VType":"Number""VMin":"0""VMax":"100"},{"Id":"0006","Type":"DoorSensor","SType":"Sensor","VType":"String""VMin":"Open""VMax":"Close"},{"Id":"0008","Type":"Alarm","SType":"Actuator","VType":"String""VMin":"Set""VMax":"Unset"}]} | Discovered Node Info {"Job":"Discovered","NodeID":"12:23:34:45:56:67","ThingList":[{"Id":"0001","Type":"Door","SType":"Actuator","VType":"String""VMin":"Open""VMax":"Close"},{"Id":"0002","Type":"Light","SType":"Actuator","VType":"String""VMin":"On""VMax":"Off"},{"Id":"0003","Type":"Presence","SType":"Sensor","VType":"String""VMin":"AtHome""VMax":"Away"},{"Id":"0004","Type":"Temperature","SType":"Sensor","VType":"Number""VMin":"-50""VMax":"50"},{"Id":"0005","Type":"Humidity","SType":"Sensor","VType":"Number""VMin":"0""VMax":"100"},{"Id":"0006","Type":"DoorSensor","SType":"Sensor","VType":"String""VMin":"Open""VMax":"Close"},{"Id":"0008","Type":"Alarm","SType":"Actuator","VType":"String""VMin":"Set""VMax":"Unset"}]} | Pass | Youk, Kwon Dongok, Min Youngkeun Jang | 1. Send discover request to Comm Manager 2. Comm Manager search SA Nodes 3. Arduino connect to IoTMS via Comm Manager. 4. Arduino send Node Info to IoTMS. 5. Comm Manager send Node Info to NodeManager
| TC_CM_SA_02 | Integration | Node Manager Comm Manager Arduino (SA Node) | Register Node | Control Msg (Send Node ID) | {"SerialNumber":"12345678","Job":"Register","Port":"3250","NodeID":"78:c4:e:1:7f:f9","URL":"192.168.1.143","Targets":["NodeManager"]} | Registered Node Info {"Job":"Registered","NodeID":"12:23:34:45:56:67","ThingList":[{"Id":"0001","Type":"Door","SType":"Actuator","VType":"String""VMin":"Open""VMax":"Close"},{"Id":"0002","Type":"Light","SType":"Actuator","VType":"String""VMin":"On""VMax":"Off"},{"Id":"0003","Type":"Presence","SType":"Sensor","VType":"String""VMin":"AtHome""VMax":"Away"},{"Id":"0004","Type":"Temperature","SType":"Sensor","VType":"Number""VMin":"-50""VMax":"50"},{"Id":"0005","Type":"Humidity","SType":"Sensor","VType":"Number""VMin":"0""VMax":"100"},{"Id":"0006","Type":"DoorSensor","SType":"Sensor","VType":"String""VMin":"Open""VMax":"Close"},{"Id":"0008","Type":"Alarm","SType":"Actuator","VType":"String""VMin":"Set""VMax":"Unset"}]} | Registered Node Info {"Job":"Registered","NodeID":"12:23:34:45:56:67","ThingList":[{"Id":"0001","Type":"Door","SType":"Actuator","VType":"String""VMin":"Open""VMax":"Close"},{"Id":"0002","Type":"Light","SType":"Actuator","VType":"String""VMin":"On""VMax":"Off"},{"Id":"0003","Type":"Presence","SType":"Sensor","VType":"String""VMin":"AtHome""VMax":"Away"},{"Id":"0004","Type":"Temperature","SType":"Sensor","VType":"Number""VMin":"-50""VMax":"50"},{"Id":"0005","Type":"Humidity","SType":"Sensor","VType":"Number""VMin":"0""VMax":"100"},{"Id":"0006","Type":"DoorSensor","SType":"Sensor","VType":"String""VMin":"Open""VMax":"Close"},{"Id":"0008","Type":"Alarm","SType":"Actuator","VType":"String""VMin":"Set""VMax":"Unset"}]} | Pass | Youk, Kwon Dongok, Min Youngkeun Jang | 1. Send register request using Node ID which is discovered from 'Discover Node action' to Comm Manager 2. Comm Manager register sending Serial Nubmer SA Nodes 3. Arduino connect to IoTMS via Comm Manager. 4. Arduino send Node Info to IoTMS. 5. Comm Manager send Node Info to NodeManager. (1~5 do on secure way using Serial Number)
| TC_NM_SA_01 | Integration | Node Manager Arduino (SA Node) | Open Door | Control Msg (Door Open Command) | {"Job":"ActionCtrl","Value":"Open","NodeID":"78:c4:e:1:7f:f9","Type":"Door","Targets":["RuleManager"],"ThingID":"0001"} | Door is opend | Door is opend | Pass | Youngkeun Jang Dongok, Min | 1. Node Manager send Command to Arduino 2. Arduino do action
| TC_NM_SA_02 | Integration | Node Manager Arduino (SA Node) | Close Door | Control Msg (Door Close Command) | {"Job":"ActionCtrl","Value":"Close","NodeID":"78:c4:e:1:7f:f9","Type":"Door","Targets":["RuleManager"],"ThingID":"0001"} | Door is closed | Door is closed | Pass | Youngkeun Jang Dongok, Min | 1. Node Manager send Command to Arduino 2. Arduino do action
| TC_NM_SA_03 | Integration | Node Manager Arduino (SA Node) | Turn on Light | Control Msg (Light On Command) | {"Job":"ActionCtrl","Value":"On","NodeID":"78:c4:e:1:7f:f9","Type":"Light","Targets":["RuleManager"],"ThingID":"0002"} | Light is turned on | Light is turned on | Pass | Youngkeun Jang Dongok, Min | 1. Node Manager send Command to Arduino 2. Arduino do action
| TC_RM_SA_04 | Integration | Node Manager Arduino (SA Node) | Turn off Light | Control Msg (Light Off Command) | {"Job":"ActionCtrl","Value":"Off","NodeID":"78:c4:e:1:7f:f9","Type":"Light","Targets":["RuleManager"],"ThingID":"0002"} | Light is turned off | Light is turned off | Pass | Youngkeun Jang Dongok, Min | 1. Node Manager send Command to Arduino 2. Arduino do action
| TC_NM_SA_05 | Integration | Node Manager Arduino (SA Node) | Get Sensors data | Polling Event | N/A | Get sensor data from Arduino | Get sensor data from Arduino | Pass | Youngkeun Jang Dongok, Min | 1. Arduino send sensor data repeatly 2. Node Managet get sensor data and check it is changed or not. 3. If there is change, Node Manage send it to RuleManager and UI. 4. If there is no changes, Node Manage ignore it.
| TC_RM_SA_01 | Integration | Rule Manager Node Manager Arduino (SA Node) | Set Alarm | Control Msg (Alarm Set Command) | {"Job":"Alarm","Value":"Setting","Targets":["RuleManager"]} | Close Door Alarm Mode Set Alarm Lamp On | Close Door Alarm Mode Set Alarm Lamp On | Pass | Bohyun, Jung | 1. Do actions if exist based on rule. 1-a. Send Door Close command to NodeManager. 2-b. NodeManager send command to Arduino 2. cancle sheduled actions if exist. (ex. If alarm unset, delete scheduled alarm set action) 3. set scheduled actions : Set Alarm Command, Set DoorCheck Command, Set Malfunction. 4. Execute schedule actions on time. 5. Get Door sensor info from NodeManager 6. If Door sensor is closed delete Malfunction action. 7. If Door sensor is opened execute Malfunction action. 8. activate/deactivate rules based on the mode.
| TC_RM_SA_02 | Integration | Rule Manager Node Manager Arduino (SA Node) | UnSet Alarm | Control Msg (Alarm USet Command) | {"Job":"Alarm","Value":"UnSet","Targets":["RuleManager"]} | Alarm Mode UnSet Alarm Lamp Off | Alarm Mode UnSet Alarm Lamp Off | Pass | Bohyun, Jung | 1. Do actions if exist based on rule. 1-a. Send AlarmLamp off command to NodeManager 1-b. NodeManager send command to Arduino 2. cancle sheduled actions if exist. (ex. If alarm unset, delete scheduled alarm set action) 3. activate/deactivate rules based on the mode.
| TC_RM_SA_03 | Integration | Rule Manager Node Manager Arduino (SA Node) | Open Door on Alarm Mode | Control Msg (Door Open Command) | {"Job":"ActionCtrl","Value":"Open","NodeID":"78:c4:e:1:7f:f9","Type":"Door","Targets":["RuleManager"],"ThingID":"0001"} | Door is not opened Send Reject Response | Door is not opened Send Reject Response | Pass | Bohyun, Jung | 1. Search action list on current condition (mode) 2. check action is on not allowed list. (ex. Do not open in alarm mode) 3. execute action if it is not blocked on rule.
| TC_RM_SA_04 | Integration | Rule Manager Node Manager Arduino (SA Node) | Get Sensors data | Polling Event | N/A | Predefined actions executed if matched rul exist. Do nothing if there is no matched rule | Predefined actions executed if matched rul exist. Do nothing if there is no matched rule | Pass | Bohyun, Jung | 1. Get sensor infos from NodeManager 2. If the thing event is defined on ruleset, then send actions event to NodeManager 2-a. NodeManager send action command to Arduino 3. Do nothing if there is no rule on the event.
| TC_NM_DB_01 | Integration | Node Manager DB | Load Nodes/Thing info | N/A | N/A | Node/Thing info is loaded from DB without error | Node/Thing info is loaded from DB without error | Pass | Dongok, Min Jonghyun, Han | 1. Load Nodes/Things info from DB
| TC_NM_DB_02 | Integration | Node Manager DB | Save Nodes/Thing Info | N/A | N/A | Node/Thing info is saved to DB without error | Node/Thing info is saved to DB without error | Pass | Dongok, Min Jonghyun, Han | 1. Save Nodes/Things info to DB
| TC_RM_DB_01 | Integration | Rule Manager DB | Load Rules | N/A | N/A | Rules are loaded from DB without error | Rules are loaded from DB without error | Pass | Bohyun, Jung Jonghyun, Han | 1. Load Rules from DB
| TC_RM_DB_02 | Integration | Rule Manager DB | Save Rules | N/A | N/A | Rules are saved to DB without error | Rules are saved to DB without error | Pass | Bohyun, Jung Jonghyun, Han | 1. Save Rules to DB
| TC_RM_DB_03 | Integration | Rule Manager DB | Load Configs | N/A | N/A | Configuration is loaded from DB without error | Configuration is loaded from DB without error | Pass | Bohyun, Jung Jonghyun, Han | 1. Load Config value from DB
| TC_RM_DB_04 | Integration | Rule Manager DB | Save Configs | N/A | N/A | Configuration is saved to DB without error | Configuration is saved to DB without error | Pass | Bohyun, Jung Jonghyun, Han | 1. Save Config Value to DB
| TC_RM_UI_01 | Integration | Rule Manager UI | Search Rules | Rule search command | {"Job":"RuleCtrl","Type":"Search","Targets":["RuleManager"]} | Return rules | Return rules | Pass | Jonghyun, Han Bohyun, Jung | 1. UI Send Search command 2. Search rules on specified condition and return matched rule. 3. Return whole rules if condition does not specified.
| TC_RM_UI_02 | Integration | Rule Manager UI | Delete Rules | Rule delete command | {"Job":"RuleCtrl","Type":"Delete","Rule":"if 78:c4:e:2:5c:a3@0001==Mail#MailBox then *@0011=POST#Message","Targets":["RuleManager"]} | Rule is deleted if it exist | Rule is deleted if it exist | Pass | Jonghyun, Han Bohyun, Jung | 1. UI Send Delete command 2. Search rules on givin condition. 3. send rules to UI
| TC_RM_UI_03 | Integration | Rule Manager UI | Add Rules | Rule add Command | {"Job":"RuleCtrl","Type":"Add","Rule":"if *@0010==Setting#Alarm then 78:c4:e:1:7f:f9@0001=Close#Door, 78:c4:e:1:7f:f9@0006=Open#DoorSensorDelay, *@0011=Malfunction#MessageDelay, *@0010=UnSet#AlarmDelay","Targets":["RuleManager"]} | Rule is added if it it not exist or it is not conflict with exist rule | Rule is added if it it not exist or it is not conflict with exist rule | Pass | Jonghyun, Han Bohyun, Jung | 1. UI send rule (condition + action string) 2. Check validity with exist rule in ruleset. (same rule, and conflict rule) 3. Return false if new rule is not valid on 1. 4. If it is new rule, create rule. 5. If there are ruls on same condition, add new actions on exist rule. 6. Update ruleset based on 4~5
| TC_RM_UI_04 | Integration | Rule Manager UI | Change Configs | Config change command | {"Job":"ConfigCtrl","Value":"0300","Type":"Alarm","Targets":["RuleManager"]} | Configuration is changed. DB is updated | Configuration is changed. DB is updated | Pass | Jonghyun, Han Bohyun, Jung | 1. UI send config value 2. Rule Manager change Config value 3. Rule which has delay action is updated. 4. Update config value in DB
Note on G2: dongog.min: Value or Set of value

## Thread Test
Thread-Test TestCases for IoTMS
| TC ID | Category | Pacakge | Function | Input | Input Value | Expected Result | Result | Pass/Fail | Test Owner | Description
| TC_01 | Thread Test | RuleManager Node Manager Arduino | Set Alarm | Control Msg (Alarm Set Command) | {"Job":"Alarm","Value":"Setting","Targets":["RuleManager"]} | 1. Door is closed. 2. Alarm is set 3. Alarm lamp is on | 1. Door is closed. 2. Alarm is set 3. Alarm lamp is on | Pass | Bohyun Jung Youngkeun Jang Jinwook Hyun | 1. Do actions if exist based on rule. 1-a. Send Door Close command to NodeManager. 2-b. NodeManager send command to Arduino 2. cancle sheduled actions if exist. (ex. If alarm unset, delete scheduled alarm set action) 3. set scheduled actions : Set Alarm Command, Set DoorCheck Command, Set Malfunction. 4. Execute schedule actions on time. 5. Get Door sensor info from NodeManager 6. If Door sensor is closed delete Malfunction action. 7. activate/deactivate rules based on the mode.
| TC_02 | Thread Test | RuleManager Node Manager Arduino | Leave Home | Remove Simson | Remove Simson | 1. Send Message to User 2. If there is no Confirm Msg with in 10s, Set Alarm 3. Turn off Lamp if it is on. | 1. Send Message to User 2. If there is no Confirm Msg with in 10s, Set Alarm 3. Turn off Lamp if it is on. | N/A | Bohyun Jung Youngkeun Jang Jinwook Hyun | 1. Arduino send event including presence senser value. 2. Node Manager check sensor value, and send it to RuleManager / UI 3. Rule Manage do action on predefined rule 3.a. Send Confirm Message to Message. 3.b. Message send message to User via Twitter (on predefined way) 4. Rule Manager set delay action on predefined rule. 4.a Set alarm with in 10s 4.b. If user send unset command, alarm set is cancled. 4.c. If user do not send unser command, do same step on TC_01 5. RUle Manager set delay action on predefined rule. 5.a Turn off lamp command to Node Manager after given time. 5.b Node Managet send command to Arduino
| TC_03 | Thread Test | RuleManager Node Manager Arduino | Someone in on Alarm Mode | Put a Thief | Put a Thief | 1. Send Emergency Message to User | 1. Send Emergency Message to User | Pass | Bohyun Jung Youngkeun Jang Jinwook Hyun | 1. Arduino send event including presence senser value. 2. Node Manager check sensor value, and send it to RuleManager / UI 3. Rule Manage do action on predefined rule 3.a. Send Emergency Message to Message. 3.b. Message send message to User via Twitter
| TC_04 | Thread Test | RuleManager Node Manager Arduino | Open Door on Alarm Mode | Open door | Open door | 1. Send Emergency Message to User | 1. Send Emergency Message to User | Pass | Bohyun Jung Youngkeun Jang Jinwook Hyun | 1. Arduino send event including door senser value. 2. Node Manager check sensor value, and send it to RuleManager / UI 3. Rule Manage do action on predefined rule 3.a. Send Emergency Message to Message. 3.b. Message send message to User via Twitter
| TC_05 | Thread Test | RuleManager Node Manager Arduino | Sensor Mal-function | Disconnect Temp/Humidity sensor | Disconnect Temp/Humidity sensor | 1. Send Mal-function message to User | 1. Send Mal-function message to User | Pass | Bohyun Jung Youngkeun Jang Jinwook Hyun | 1. Arduino send event including temp/humidity senser value. 2. Node Manager check sensor value, and send it to RuleManager / UI 3. Rule Manage do action on predefined rule 3.a. Send Mal-function Message to Message. 3.b. Message send message to User via Twitter
| TC_06 | Thread Test | RuleManager Node Manager Arduino | Set Alarm mode, but Door does not closed | Control Msg (Alarm Set Command) Put something on door | {"Job":"Alarm","Value":"Setting","Targets":["RuleManager"]} | 1. Door is not closed 2. Send Mal-function message to user | 1. Door is not closed 2. Send Mal-function message to user | Pass | Bohyun Jung Youngkeun Jang Jinwook Hyun | 1. Do actions if exist based on rule. 1-a. Send Door Close command to NodeManager. 2-b. NodeManager send command to Arduino 2. cancle sheduled actions if exist. (ex. If alarm unset, delete scheduled alarm set action) 3. set scheduled actions : Set Alarm Command, Set DoorCheck Command, Set Malfunction. 4. Execute schedule actions on time. 5. Get Door sensor info from NodeManager 6. Do Mal-function action. 6.a. Send Mal-function Message to Message. 6.b. Message send message to User via Twitter 8. UnSet Alarm 9. activate/deactivate rules based on the mode.
| TC_07 | Thread Test | RuleManager Node Manager Arduino | Connect Second SA Node | Discover / Register Command | {"Job":"Discover","Duration":"20","Targets":["NodeManager"]} {"SerialNumber":"12345679","Job":"Register","Port":"3250","NodeID":78:c4:e:2:5c:a3","URL":"192.168.1.143","Targets":["NodeManager"]} | 1. Second node is discoved. 2. Second node is registered | 1. Second node is discoved. 2. Second node is registered | Pass | Bohyun, Jung Jinwook Hyun Youngkeun Jang | 1. Send discover request to Comm Manager 2. Comm Manager search SA Nodes 3. Arduino connect to IoTMS via Comm Manager. 4. Arduino send Node Info to IoTMS. 5. Comm Manager send Node Info to NodeManager
Note on G2: dongog.min: Value or Set of value

## System Test
System-Test TestCases for IoTMS
| TC ID | Category | Pacakge | Function | Input | Input Value | Expected Result | Result | Pass/Fail | Test Owner | Description
| TC_01 | Thread Test | UI RuleManager Node Manager Arduino | Set Alarm | User set 'Alarm on' via laptop or mobile phone | {"Job":"Alarm","Value":"Setting","Targets":["RuleManager"]} | 1. Door is closed. 2. Alarm is set 3. Alarm lamp is on | 1. Door is closed. 2. Alarm is set 3. Alarm lamp is on | Pass | Jonghyun Han Bohyun Jung Youngkeun Jang Jinwook Hyun | 1. User Log-in the system 2. Usesr click "Alarm on" command on web page 3. Do actions if exist based on rule. a. Send Door Close command to NodeManager. b. NodeManager send command to Arduino 4. cancle sheduled actions if exist. (ex. If alarm unset, delete scheduled alarm set action) 5. set scheduled actions : Set Alarm Command, Set DoorCheck Command, Set Malfunction. 6. Execute schedule actions on time. 7. Get Door sensor info from NodeManager 8. If Door sensor is closed delete Malfunction action. 9. activate/deactivate rules based on the mode.
| TC_02 | Thread Test | UI RuleManager Node Manager Arduino | Leave Home | Remove Simson | Remove Simson | 1. Send Message to User 2. If there is no Confirm Msg with in 10s, Set Alarm 3. Turn off Lamp if it is on. | 1. Send Message to User 2. If there is no Confirm Msg with in 10s, Set Alarm 3. Turn off Lamp if it is on. | N/A | Jonghyun Han Bohyun Jung Youngkeun Jang Jinwook Hyun | 1. Arduino send event including presence senser value. 2. Node Manager check sensor value, and send it to RuleManager / UI 3. Rule Manage do action on predefined rule 3.a. Send Confirm Message to Message. 3.b. Message send message to User via Twitter (on predefined way) 4. Rule Manager set delay action on predefined rule. 4.a Set alarm with in 10s 4.b. If user send unset command, alarm set is cancled. 4.c. If user do not send unser command, do same step on TC_01 5. Rule Manager set delay action on predefined rule. 5.a Turn off lamp command to Node Manager after given time. 5.b Node Managet send command to Arduino
| TC_03 | Thread Test | UI RuleManager Node Manager Arduino | Someone in on Alarm Mode | Put a Thief | Put a Thief | 1. Send Emergency Message to User 2. sensor value is updated on web page | 1. Send Emergency Message to User 2. sensor value is updated on web page | Pass | Bohyun Jung Youngkeun Jang Jinwook Hyun | 1. Arduino send event including presence senser value. 2. Node Manager check sensor value, and send it to RuleManager / UI 3. Rule Manage do action on predefined rule 3.a. Send Emergency Message to Message. 3.b. Message send message to User via Twitter 4. User get message via Twitter. 5. User log in the system 6. User can check value though web page.
| TC_04 | Thread Test | UI RuleManager Node Manager Arduino | Door is opened on Alarm Mode | Open door | Open door | 1. Send Emergency Message to User 2. sensor value is updated on web page | 1. Send Emergency Message to User 2. sensor value is updated on web page | Pass | Bohyun Jung Youngkeun Jang Jinwook Hyun | 1. Arduino send event including door senser value. 2. Node Manager check sensor value, and send it to RuleManager / UI 3. Rule Manage do action on predefined rule 3.a. Send Emergency Message to Message. 3.b. Message send message to User via Twitter 4. User get message via Twitter. 5. User can check value though web pa
| TC_05 | Thread Test | UI RuleManager Node Manager Arduino | Sensor Mal-function | Disconnect Temp/Humidity sensor | Disconnect Temp/Humidity sensor | 1. Send Mal-function message to User 2. Sensor value is updated on web page | 1. Send Mal-function message to User 2. Sensor value is updated on web page | Pass | Bohyun Jung Youngkeun Jang Jinwook Hyun | 1. Arduino send event including temp/humidity senser value. 2. Node Manager check sensor value, and send it to RuleManager / UI 3. Rule Manage do action on predefined rule 3.a. Send Mal-function Message to Message. 3.b. Message send message to User via Twitter 4. User get message via Twitter. 5. User log in the system 6. User can check value though web page.
| TC_06 | Thread Test | UI RuleManager Node Manager Arduino | Set Alarm mode, but Door does not closed | User set 'Alarm on' via laptop or mobile phone Put something on door | {"Job":"Alarm","Value":"Setting","Targets":["RuleManager"]} | 1. Door is not closed 2. Send Mal-function message to user 3. sensor value is updated on web page | 1. Door is not closed 2. Send Mal-function message to user 3. sensor value is updated on web page | Pass | Jonghyun Han Bohyun Jung Youngkeun Jang Jinwook Hyun | 1. Do actions if exist based on rule. 1-a. Send Door Close command to NodeManager. 2-b. NodeManager send command to Arduino 2. cancle sheduled actions if exist. (ex. If alarm unset, delete scheduled alarm set action) 3. set scheduled actions : Set Alarm Command, Set DoorCheck Command, Set Malfunction. 4. Execute schedule actions on time. 5. Get Door sensor info from NodeManager 6. Do Mal-function action. 6.a. Send Mal-function Message to Message. 6.b. Message send message to User via Twitter 8. UnSet Alarm 9. activate/deactivate rules based on the mode. 10. User get message via Twitter. 11. User log in the system 12. User can check value though web page.
| TC_07 | Thread Test | UI RuleManager Node Manager Arduino | Connect Second SA Node | User set 'discover' via laptop or mobile phone | {"Job":"Discover","Duration":"20","Targets":["NodeManager"]} {"SerialNumber":"12345679","Job":"Register","Port":"3250","NodeID":78:c4:e:2:5c:a3","URL":"192.168.1.143","Targets":["NodeManager"]} | 1. Second node is discoved. 2. Second node is registered 3. Node/thing info is displayed on web page | 1. Second node is discoved. 2. Second node is registered 3. Node/thing info is displayed on web page | Pass | Jonghyun Han Bohyun Jung Youngkeun Jang Jinwook Hyun | 1. Send discover request to Comm Manager 2. Comm Manager search SA Nodes 3. Arduino connect to IoTMS via Comm Manager. 4. Arduino send Node Info to IoTMS. 5. Comm Manager send Node Info to NodeManager 6. User log in the system. 7. User can check Node/Thing info on web page
| TC_08 | Thread Test | UI RuleManager Arduino DB | Open Door on Alarm Mode | User click open door command via laptop or mobile | {"Job":"ActionCtrl","Value":"Open","NodeID":"78:c4:e:1:7f:f9","Type":"Door","Targets":["RuleManager"],"ThingID":"0001"} | 1. Door is not opend. 2. Error message is displayed on web page | 1. Door is not opend. 2. Error message is displayed on web page | N/A | Jonghyun Han Bohyun Jung Youngkeun Jang Jinwook Hyun | 1. User Log-in the system 2. Usesr click "Door Open" command on web page 3. Door is not opened. 4. Reject message is shown on web page
| TC_09 | Thread Test | UI DB | Check log info | User click "log info" via laptop or mobile | N/A | 1. Log info is displayed on web page | 1. Log info is displayed on web page | N/A | Jonghyun Han Bohyun Jung Youngkeun Jang Jinwook Hyun | 1. User log-in the system. 2. User click "log info" on web page. 3. UI search log info from DB 4. UI display log info on web page
| TC_10 | Thread Test | UI RuleManager | Change config value | User click "config" via laptop or mobile phone | {"Job":"ConfigCtrl","Value":"0300","Type":"Alarm","Targets":["RuleManager"]} | 1. configuration is changed. 2. changed value is displayed on web page | 1. configuration is changed. 2. changed value is displayed on web page | Pass | Jonghyun Han Bohyun Jung | 1. User log-in the system. 2. User click "config" on web page. 3. UI send Config event to RuleManager. 4. RuleManager change config value. 5. RuleManager update config value on DB. 6. UI display changed value on web page
| TC_11 | Thread Test | UI RuleManager | Add new rule | User add rule via laptop or mobie phone | {"Job":"RuleCtrl","Type":"Add","Rule":"if *@0010==Setting#Alarm then 78:c4:e:1:7f:f9@0001=Close#Door, 78:c4:e:1:7f:f9@0006=Open#DoorSensorDelay, *@0011=Malfunction#MessageDelay, *@0010=UnSet#AlarmDelay","Targets":["RuleManager"]} | 1. Rule is added. 2. added rule is displayed on web page | 1. Rule is added. 2. added rule is displayed on web page | Pass | Jonghyun Han Bohyun Jung | 1. User log-in the system. 2. User click "log info" on web page. 3. UI search log info from DB 4. UI display log info on web page
| TC_12 | Thread Test | UI Node Manager Arduino | Remove Node | User click "remove node" via laptop or movile phone | N/A | 1. Node is removed. 2. Node/Thing info is updated on web page | 1. Node is removed. 2. Node/Thing info is updated on web page | N/A | Jonghyun Han Dongok Min Youngkeun Jang Jinwook Hyun | 1. User log-in the system. 2. User click "rule add" on web page. 3. UI send add rule message to RuleManager. 4. RuleManager add rule if it is not exist and not conflicted. 5. UI send search rule message to RuleManager. 6. RuleManager send rules to UI. 7. UI display rule info on web page
Note on G2: dongog.min: Value or Set of value