## EVM
Date | On Each Date |  |  | Stacked
| Plan | Actual Cost | Earned Point | Plan | Actual Cost | Earned Value | Earned Point
2015-05-07 | 12 | 12 | 0 | 12 | 12 | 0 | 0
2015-05-08 | 0 | 0 | 0 | 12 | 12 | 0 | 0
2015-05-09 | 3 | 3 | 0 | 15 | 15 | 0 | 0
2015-05-10 | 0 | 0 | 0 | 15 | 15 | 0 | 0
2015-05-11 | 0 | 0 | 0 | 15 | 15 | 0 | 0
2015-05-12 | 9 | 24 | 10 | 24 | 39 | 58.8 | 10
2015-05-13 | 6 | 3 | 1 | 30 | 42 | 64.68 | 11
2015-05-14 | 6 | 12 | 3 | 36 | 54 | 82.32 | 14
2015-05-15 | 0 | 0 | 0 | 36 | 54 | 82.32 | 14
2015-05-16 | 0 | 0 | 0 | 36 | 54 | 82.32 | 14
2015-05-17 | 0 | 0 | 0 | 36 | 54 | 82.32 | 14
2015-05-18 | 0 | 3 | 0 | 36 | 57 | 82.32 | 14
2015-05-19 | 0 | 0 | 0 | 36 | 57 | 82.32 | 14
2015-05-20 | 12 | 12 | 0 | 48 | 69 | 82.32 | 14
2015-05-21 | 0 | 0 | 0 | 48 | 69 | 82.32 | 14
2015-05-22 | 0 | 0 | 0 | 48 | 69 | 82.32 | 14
2015-05-23 | 0 | 0 | 0 | 48 | 69 | 82.32 | 14
2015-05-24 | 0 | 12 | 0 | 48 | 81 | 82.32 | 14
2015-05-25 | 18 | 42 | 0 | 66 | 123 | 82.32 | 14
2015-05-26 | 18 | 0 | 0 | 84 | 123 | 82.32 | 14
2015-05-27 | 18 | 4 | 0 | 102 | 127 | 82.32 | 14
2015-05-28 | 18 | 84 | 3 | 120 | 211 | 99.96 | 17
2015-05-29 | 18 | 0 | 0 | 138 | 211 | 99.96 | 17
2015-05-30 | 0 | 0 | 0 | 138 | 211 | 99.96 | 17
2015-05-31 | 0 | 77 | 0 | 138 | 288 | 99.96 | 17
2015-06-01 | 18 | 18 | 3 | 156 | 306 | 117.6 | 20
2015-06-02 | 24 | 6 | 6 | 180 | 312 | 152.88 | 26
2015-06-03 | 24 | 4 | 2 | 204 | 316 | 164.64 | 28
2015-06-04 | 24 | 0 | 0 | 228 | 316 | 164.64 | 28
2015-06-05 | 24 | 6 | 0 | 252 | 322 | 164.64 | 28
2015-06-06 | 0 | 0 | 0 | 252 | 322 | 164.64 | 28
2015-06-07 | 0 | 54 | 2 | 252 | 376 | 176.4 | 30
2015-06-08 | 24 | 30 | 4 | 276 | 406 | 199.92 | 34
2015-06-09 | 24 | 24 | 2 | 300 | 430 | 211.68 | 36
2015-06-10 | 24 | 11 | 3 | 324 | 441 | 229.32 | 39
2015-06-11 | 24 | 0 | 0 | 348 | 441 | 229.32 | 39
2015-06-12 | 24 | 0 | 0 | 372 | 441 | 229.32 | 39
2015-06-13 | 0 | 54 | 6 | 372 | 495 | 264.6 | 45
2015-06-14 | 0 | 54 | 3 | 372 | 549 | 282.24 | 48
2015-06-15 | 24 | 42 | 24 | 396 | 591 | 423.36 | 72
2015-06-16 | 24 | 18 | 0 | 420 | 609 | 423.36 | 72
2015-06-17 | 24 | 46 |  | 444 | 655 | 423.36 | 72
2015-06-18 | 24 | 0 |  | 468 | 655 | 423.36 | 72
2015-06-19 | 24 | 30 | 3 | 492 | 685 | 441 | 75
2015-06-20 | 0 | 24 | 3 | 492 | 709 | 458.64 | 78
2015-06-21 | 0 | 18 | 2 | 492 | 727 | 470.4 | 80
2015-06-22 | 24 | 18 | 0 | 516 | 745 | 470.4 | 80
2015-06-23 | 24 | 48 | 4 | 540 | 793 | 493.92 | 84
2015-06-24 | 24 |  |  | 564
2015-06-25 | 24 |  |  | 588

## WBS
System | 1Level | 2Level | 3Level | Value (pt) | Charge | Startdate (mm/dd) | EndDate (mm/dd)
IoTMS | Planning(5pt) | Team Building |  | 1 | All | 2015-05-12 | 2015-05-12
|  | Project scope |  | 1 | All | 2015-05-07 | 2015-05-13
|  | Requirement |  | 1 | All | 2015-05-12 | 2015-05-12
|  | Overall Schedule |  | 1 | All | 2015-05-12 | 2015-05-12
|  | Risk analysis |  | 1 | All | 2015-05-12 | 2015-05-12
| Architectureral Driver(15pt) | Functional Requirement | Use Case | 1 | All | 2015-05-12 | 2015-05-12
|  |  | FBS | 2 | All | 2015-05-12 | 2015-05-12
|  | Business Constraint |  | 1 | All | 2015-05-12 | 2015-05-12
|  | Technical Constraint |  | 1 | All | 2015-05-12 | 2015-05-12
|  | Quality Attribute |  | 3 | All | 2015-05-12 | 2015-05-14
|  | System Context |  | 1 | All | 2015-05-12 | 2015-05-12
|  | Architectureral Driver Presentation Update |  | 2 | All | 2015-05-24 | 2015-05-28
|  | Architectureral Driver refine | Functional Requirement refine | 1 | Kwan | 2015-05-28 | 2015-05-28
|  |  | Quality Attribute refine | 2 | All | 2015-06-02 | 2015-06-02
|  |  | System Context refine | 1 | Jang | 2015-06-02 | 2015-06-02
| Design(20pt) | Static Perspective(8pt) | Module View | 3 | All | 2015-05-25 | 2015-06-02
|  |  | Review ModuleView | 2 | All | 2015-06-03 | 2015-06-03
|  |  | Feasubility Experiement | 3 | Han,Hyun | 2015-05-29 | 2015-06-01
|  | Dynamic Perspective(8pt) | C&C View | 3 | All | 2015-06-05 | 2015-06-08
|  |  | Sequencial View | 3 | All | 2015-06-09 | 2015-06-09
|  |  | Feasubility Experiement | 2 | All | 2015-06-07 | 2015-06-07
|  | Pysical Perspective(4pt) | Module Allocation View | 2 | All | 2015-06-09 | 2015-06-09
|  |  | Review Design | 2 | All | 2015-06-10 | 2015-06-10
| Implementation(40pt) | Server - Arduino Communication | Protocol | 1 | Kwan | 2015-06-08 | 2015-06-08
|  |  | Arduino Communication function | 1 | Jang | 2015-06-13 | 2015-06-15
|  |  | Server Communication Module | 1 | Kwan | 2015-06-13 | 2015-06-15
|  | Main Frame | Main Frame Design | 1 | Han | 2015-06-13 | 2015-06-14
|  |  | Prototype Main Frame | 0 | Han | 2015-06-13 | 2015-06-14
|  | Database | Data Analysis | 1 | Han | 2015-06-14 | 2015-06-17
|  |  | DB Table Design | 0 | Han | 2015-06-14 | 2015-06-17
|  | Event Bus | Event Bus research | 0 | Hyun | 2015-06-08 | 2015-06-08
|  |  | Event Bus Experiment | 1 | Hyun | 2015-06-08 | 2015-06-08
|  |  | Event Bus implement | 1 | Hyun | 2015-06-10 | 2015-06-10
|  |  | Event Bus Test | 1 | Hyun | 2015-06-13 | 2015-06-13
|  | Node, Sensor/Actuator Monitor | Communication Manager | 1 | Kwan | 2015-06-13 | 2015-06-15
|  |  | Node Manager | 1 | Min | 2015-06-13 | 2015-06-15
|  |  | UI Monitoring Controller | 1 | Han | 2015-06-15 | 2015-06-15
|  |  | UI Monitoring View | 1 | Han | 2015-06-15 | 2015-06-15
|  |  | Each Module Test | 1 | Min,Jung | 2015-06-15 | 2015-06-15
|  | Actuator Contol | Communication Manager | 1 | Kwan | 2015-06-13 | 2015-06-15
|  |  | Node Manager | 1 | Min | 2015-06-13 | 2015-06-15
|  |  | UI Control Controller | 1 | Han | 2015-06-15 | 2015-06-15
|  |  | UI Control View | 1 | Han | 2015-06-15 | 2015-06-15
|  |  | Each Module Test | 1 | Min,Jung | 2015-06-16 | 2015-06-19
|  | Node Query, Sensor/Actuator Query | Communication Manager | 1 | Kwan | 2015-06-13 | 2015-06-15
|  |  | Node Manager | 1 | Min | 2015-06-13 | 2015-06-15
|  |  | UI Query Controller | 1 | Han | 2015-06-15 | 2015-06-19
|  |  | UI Query View | 0 | Han | 2015-06-15 | 2015-06-19
|  |  | Each Module Test | 1 | Min,Jung | 2015-06-15 | 2015-06-15
|  | Node Register/Remove | Communication Manager | 1 | Kwan | 2015-06-13 | 2015-06-15
|  |  | Node Manager | 1 | Min | 2015-06-13 | 2015-06-15
|  |  | Rule Manger | 1 | Jung | 2015-06-13 | 2015-06-15
|  |  | UI Node Register/Remove Controller | 1 | Han | 2015-06-16 | 2015-06-23
|  |  | UI Node Register/Remove View | 0 | Han | 2015-06-16 | 2015-06-23
|  |  | Each Module Test | 1 | Min,Jung | 2015-06-13 | 2015-06-15
|  | Message | Message Define | 1 | Kwan | 2015-06-13 | 2015-06-13
|  |  | Message Manager | 1 | Jung | 2015-06-13 | 2015-06-13
|  |  | Message Make/Send module | 1 | Jung | 2015-06-13 | 2015-06-13
|  | History | UI History Controller | 1 | Han | 2015-06-13 | 2015-06-13
|  |  | UI History View | 0 | Han | 2015-06-13 | 2015-06-13
|  |  | History DB Query Design | 0 | Han | 2015-06-13 | 2015-06-13
|  |  | Module Test | 1 | Han | 2015-06-13 | 2015-06-13
|  | RuleSet | Communication Manager | 1 | Kwn | 2015-06-13 | 2015-06-15
|  |  | Node Manager | 1 | Min | 2015-06-13 | 2015-06-15
|  |  | Rule Manger | 1 | Jung | 2015-06-10 | 2015-06-15
|  |  | Message Manager | 1 | Han | 2015-06-13 | 2015-06-20
|  |  | UI RuleSet Controller | 1 | Han | 2015-06-13 | 2015-06-15
|  |  | UI RuleSet View | 0 | Han | 2015-06-13
|  |  | Each Module Test | 1 | Jung | 2015-06-15 | 2015-06-15
|  | User Management | UI User Controller | 1 | Han
|  | (Login, adduser, deluser) | UI User View | 0 | Han
|  |  | User DB Query Design | 0 | Han
|  |  | Each Module Test | 1 | Han
|  | Setting | UI Setting Controller | 1 | Han | 2015-06-13 | 2015-06-14
|  |  | UI Setting View | 0 | Han | 2015-06-13 | 2015-06-14
|  |  | Setting DB Query Design | 0 | Han | 2015-06-13 | 2015-06-14
|  |  | Each Module Test | 1 | Han | 2015-06-13 | 2015-06-14
| Test(10pt) |  | integration test #1 | 2 | All | 2015-06-20 | 2015-06-20
|  |  | integration test #2 | 2 | All | 2015-06-21 | 2015-06-21
|  |  | integration test #3 | 2 | All | 2015-06-23 | 2015-06-23
|  |  | integration test #4 | 2 | All
| Final Document(8pt) | Final presentation | Doc. structure | 1 | All | 2015-06-23 | 2015-06-23
|  |  | Make doc & integration | 3 | All | 2015-06-23
|  | Architecture Design Doc | Doc. structure | 1 | All | 2015-06-19 | 2015-06-19
|  |  | Make doc & integration | 3 | All | 2015-06-20

## time log
e
start time | end time | place | item | Stage | Task | Description | time spent | [6 empty] | output document
[7 empty] | JH Han | Y Kwon | DW Min | BH Jung | YG Jang | JW Hyun | total |  |  | JH Han | Y Kwon | DW Min | BH Jung | YG Jang | JW Hyun | total
2015-05-07 18:00 | 2015-05-07 20:00 | LGE / Pyeongtaek-si / Korea | meeting 1st in Korea | Plan | Project scope | Projent Descrption review | 2 | 2 | 2 | 2 | 2 | 2 | 12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-05-10 | [5 empty] | total | 2 | 2 | 2 | 2 | 2 | 2 | 12 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 12
2015-05-10 18:00 | 2015-05-07 21:00 | LGE / Pyeongtaek-si / Korea | Documentation | Plan | Project scope | Make presentation | 3 | 0 | 0 | 0 | 0 | 0 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 3 | 0 | 0 | 0 | 0 | 0 | 3 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 3
2015-05-12 18:00 | 2015-05-12 22:00 | LGE / Pyeongtaek-si / Korea | meeting 2nd in Korea | Plan | Team Building | Confirm roles and responsibility of each members | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | Plan | Overall Schedule | Set up a plan of schedule | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | analysis | requirement | Find out functional requirement | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | analysis | use case scenario | Make sample use-case scenarios | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | analysis | Risk analysis | Analyze risks of project | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | analysis | constraint | Find out constraint | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | analysis | quality attribute | Find out quality attributes | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | analysis | Work Break Down | Tear down project work task | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 4 | 4 | 4 | 4 | 4 | 4 | 24 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 24
2015-05-13 18:00 | 2015-05-13 21:00 | LGE / Pyeongtaek-si / Korea | Documentation | Plan | Project scope | Make presentation | 3 | 0 | 0 | 0 | 0 | 0 | 3 | IoT System Initial Presentation_0512.pptx |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 3 | 0 | 0 | 0 | 0 | 0 | 3 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 3
2015-05-14 18:00 | 2015-05-14 20:00 | LGE / Pyeongtaek-si / Korea | meeting 3rd in Korea | Plan | Team Building | Modify roles and responsibility of each members | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | analysis | quality attribute | Make quality attributes scenarios | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | analysis | feasibility | Check spec. of Arduino and IDE | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | analysis | Work Break Down | Tear down project work task | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 2 | 2 | 2 | 2 | 2 | 2 | 12 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 12
2015-05-18 18:00 | 2015-05-18 21:00 | LGE / Pyeongtaek-si / Korea | Documentation | Plan | ADS draft & plan | Send presentation(draft plans and ADS document) to mentor | 3 | 0 | 0 | 0 | 0 | 0 | 3 | IoT System Initial Presentation_0518.pptx |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 3 | 0 | 0 | 0 | 0 | 0 | 3 |  |  | 3 | 0 | 0 | 0 | 0 | 0 | 3
2015-05-20 17:00 | 2015-05-20 19:00 | LGE / Pyeongtaek-si / Korea | meeting 4th in Korea | analysis | feasibility | Review IoT server system function | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 | IoT System Initial Presentation_0520.pptx |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | analysis | use case scenario | Add use-case description | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | analysis | quality attribute | Add quality attributes description | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | analysis | glossary | Define SA node | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 2 | 2 | 2 | 2 | 2 | 2 | 12 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 12
2015-05-24 20:30 | 2015-05-24 22:30 | Shadyside Inn | Documentation | Plan | ADS draft & plan | Review the feedback of document from mentor | 2 | 2 | 2 | 2 | 2 | 2 | 12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 2 | 2 | 2 | 2 | 2 | 2 | 12 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 12
2015-05-25 14:30 | 2015-05-25 17:30 | Shadyside Inn | meeting 1st in Pittsburgh | Plan | ADS draft & plan | Update ADS draft & plan | 3 | 3 | 3 | 3 | 3 | 3 | 18 | IoT System Initial Presentation_0526.pptx |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-05-25 20:00 | 2015-05-25 23:00 |  |  | Design | domain model | make domain model draft | 3 | 3 | 3 | 3 | 3 | 3 | 18 | project_requirement_v2.pptx |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-05-25 23:00 | 2015-05-25 12:00 |  |  | Design | module view | make module view draft | 1 | 1 | 1 | 1 | 1 | 1 | 6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 7 | 7 | 7 | 7 | 7 | 7 | 42 |  |  | 7 | 7 | 7 | 7 | 7 | 7 | 42
2015-05-27 15:00 | 2015-05-27 15:40 | CMU | meeting 1st with mentor | mentoring | ADS draft & plan | review ADS draft & plan | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 4 |  |  | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 4
2015-05-28 20:00 | 2015-05-27 23:00 | Shadyside Inn | meeting 2nd in Pittsburgh | Plan | ADS draft & plan | prepare presentatinon of ADS draft & plan | 3 | 3 | 3 | 3 | 3 | 3 | 18 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 3 | 3 | 3 | 3 | 3 | 3 | 18 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 18
2015-05-28 14:00 | 2015-05-27 18:00 | Shadyside Inn | meeting 3rd Pittsburgh | analysis | requirement | update functional requirement | 6 | 6 | 6 | 6 | 6 | 6 | 36 | project_requirement_v2_1.pptx |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-05-28 20:00 | 2015-05-28 01:00 | Shadyside Inn | meeting 3rd Pittsburgh | analysis | domain model | update system context | 5 | 5 | 5 | 5 | 5 | 5 | 30 | ProjectMeeting150530_Sketch.pptx |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 11 | 11 | 11 | 11 | 11 | 11 | 66 |  |  | 11 | 11 | 11 | 11 | 11 | 11 | 66
2015-05-31 09:00 | 2015-05-31 17:00 | Shadyside Inn | meeting 4th Pittsburgh | Design | class diagram | Design User Interface module | 8 | 8 | 0 | 0 | 0 | 0 | 16 | Y Kwon : User Interface scenario PPT JH Han : feasibility sdudy for UI |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-05-31 09:00 | 2015-05-31 17:00 | Shadyside Inn | meeting 4th Pittsburgh | Design | class diagram | Design Node / Link module | 0 | 0 | 8 | 0 | 8 | 0 | 16 | Node/Link class diagram initial draft PPT |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-05-31 09:00 | 2015-05-31 17:00 | Shadyside Inn | meeting 4th Pittsburgh | Design | class diagram | Design Rule set module | 0 | 0 | 0 | 8 | 0 | 0 | 8 | Rule manager class diagram initial draft PPT Rule set format initial draft |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-05-31 09:00 | 2015-05-31 17:00 | Shadyside Inn | meeting 4th Pittsburgh | Design | class diagram | Design Event Bus module | 0 | 0 | 0 | 0 | 0 | 8 | 8 | feasibility sdudy for Eventbus & json |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-05-31 17:00 | 2015-05-31 18:00 | Shadyside Inn | meeting 4th Pittsburgh | analysis | requirement | Review User Interface scenario | 1 | 1 | 1 | 1 | 1 | 1 | 6 | Ask Tony about global/local secure mode |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-05-31 19:30 | 2015-05-31 20:30 | Shadyside Inn | meeting 4th Pittsburgh | analysis | requirement | Review functional requirement / quality attribute( for ask Tony ) | 1 | 1 | 1 | 1 | 1 | 1 | 6 | e-mail to Tony |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-05-31 20:30 | 2015-05-31 22:30 | Shadyside Inn | meeting 4th Pittsburgh | Design | class diagram | Review User Interface module | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shadyside Inn | meeting 4th Pittsburgh |  |  | Review Rule set module | 0.5 | 1 | 1 | 1 | 1 | 1 | 5.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shadyside Inn | meeting 4th Pittsburgh |  |  | Review Node / Link module | 0.5 | 1 | 1 | 1 | 1 | 1 | 5.5 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | Shadyside Inn | meeting 4th Pittsburgh |  |  | Review Event Bus module | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 12 | 13 | 13 | 13 | 13 | 13 | 77 |  |  | 12 | 13 | 13 | 13 | 13 | 13 | 77
2015-06-01 19:30 | 2015-06-01 20:30 | Shadyside Inn | meeting 5th Pittsburgh | Design | class diagram | review Event Bus sample code | 1 | 1 | 1 | 1 | 1 | 1 | 6 | Event Bus sample code |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-01 20:30 | 2015-06-01 22:30 | Shadyside Inn | meeting 5th Pittsburgh | Design | class diagram | Design module view | 2 | 2 | 2 | 2 | 2 | 2 | 12 | module view ongoing |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 3 | 3 | 3 | 3 | 3 | 3 | 18 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 18
2015-06-02 19:30 | 2015-06-01 22:30 | Shadyside Inn | meeting 6th Pittsburgh | Design | class diagram | Design module view | 1 | 1 | 1 | 1 | 1 | 1 | 6 | Design module view |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 1 | 1 | 1 | 1 | 1 | 1 | 6 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 6
2015-06-03 12:30 | 2015-06-03 13:10 | CMU | meeting 2nd with mentor | mentoring | class diagram | review Design module view | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 4 |  |  | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 4
2015-06-05 16:00 | 2015-06-05 17:00 | Shadyside Inn | meeting 7th Pittsburgh | implementation | dynamic view | initialize event message protocol | 1 | 1 | 1 | 1 | 1 | 1 | 6 | interaction.xlsx |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 1 | 1 | 1 | 1 | 1 | 1 | 6 |  |  | 1 | 1 | 1 | 1 | 1 | 1 | 6
2015-06-07 09:00 | 2015-06-07 18:00 | Shadyside Inn | Experiment | implementation | event bus | make sample code | 0 | 0 | 0 | 0 | 0 | 9 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-07 09:00 | 2015-06-07 18:00 | Shadyside Inn | Experiment | implementation | rule manager | make sample code | 0 | 0 | 0 | 9 | 0 | 0 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-07 09:00 | 2015-06-07 18:00 | Shadyside Inn | Experiment | implementation | UI | make sample code | 9 | 0 | 0 | 0 | 0 | 0 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-07 09:00 | 2015-06-07 18:00 | Shadyside Inn | Experiment | implementation | event message protocol | update event message protocol | 0 | 9 | 0 | 0 | 0 | 0 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-07 09:00 | 2015-06-07 18:00 | Shadyside Inn | Experiment | implementation | Arduino | make sample code | 0 | 0 | 0 | 0 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-07 09:00 | 2015-06-07 18:00 | Shadyside Inn | Experiment | implementation | node manager | make sample code | 0 | 0 | 9 | 0 | 0 | 0 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 9 | 9 | 9 | 9 | 9 | 9 | 54 |  |  | 9 | 9 | 9 | 9 | 9 | 9 | 54
2015-06-08 14:00 | 2015-06-08 16:00 | Shadyside Inn | meeting 8th Pittsburgh | implementation | implementation | sample code review upload sample code to GitHub | 2 | 2 | 2 | 2 | 2 | 2 | 12 | https://github.com/youkkwon/smarthome |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-08 16:00 | 2015-06-08 17:00 | Shadyside Inn | meeting 8th Pittsburgh | Design | dynamic view | make dynamic view | 1 | 1 | 1 | 1 | 1 | 1 | 6 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 3 | 3 | 3 | 3 | 3 | 3 | 18 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 18
2015-06-08 19:00 | 2015-06-08 21:00 | Shadyside Inn | Experiment | implementation | event bus | make sample code | 0 | 0 | 0 | 0 | 0 | 2 | 2 | https://github.com/youkkwon/smarthome |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-08 19:00 | 2015-06-08 21:00 | Shadyside Inn | Experiment | implementation | rule manager | make sample code | 0 | 0 | 0 | 2 | 0 | 0 | 2 | https://github.com/youkkwon/smarthome |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-08 19:00 | 2015-06-08 21:00 | Shadyside Inn | Experiment | implementation | UI | make sample code | 2 | 0 | 0 | 0 | 0 | 0 | 2 | https://github.com/youkkwon/smarthome |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-08 19:00 | 2015-06-08 21:00 | Shadyside Inn | Experiment | implementation | communication manager | update event message protocol | 0 | 2 | 0 | 0 | 0 | 0 | 2 | https://github.com/youkkwon/smarthome |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-08 19:00 | 2015-06-08 21:00 | Shadyside Inn | Experiment | implementation | Arduino | make sample code | 0 | 0 | 0 | 0 | 2 | 0 | 2 | https://github.com/youkkwon/smarthome |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-08 19:00 | 2015-06-08 21:00 | Shadyside Inn | Experiment | implementation | node manager | make sample code | 0 | 0 | 2 | 0 | 0 | 0 | 2 | https://github.com/youkkwon/smarthome |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 2 | 2 | 2 | 2 | 2 | 2 | 12 |  |  | 2 | 2 | 2 | 2 | 2 | 2 | 12
2015-06-09 14:00 | 2015-06-09 17:00 | Shadyside Inn | meeting 9th Pittsburgh | implementation | implementation | sample code review | 2 | 2 | 2 | 2 | 2 | 2 | 12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-09 19:00 | 2015-06-09 21:00 | Shadyside Inn | meeting 9th Pittsburgh | Design | dynamic view | make dynamic view | 2 | 2 | 2 | 2 | 2 | 2 | 12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 4 | 4 | 4 | 4 | 4 | 4 | 24 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 24
2015-06-10 12:30 | 2015-06-10 13:10 | CMU | meeting 3rd with mentor | mentoring | class diagram | review Design module view | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 4 |  |  | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 4
2015-06-10 15:00 | 2015-06-10 22:00 | Shadyside Inn | Experiment | implementation | rule manager | implementation | 0 | 0 | 0 | 7 | 0 | 0 | 7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 0 | 0 | 0 | 7 | 0 | 0 | 7 |  |  | 0 | 0 | 0 | 7 | 0 | 0 | 7
2015-06-13 09:00 | 2015-06-13 18:00 | Shadyside Inn | Experiment | implementation | Arduino | implementation | 0 | 0 | 0 | 0 | 0 | 9 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-13 09:00 | 2015-06-13 18:00 | Shadyside Inn | Experiment | implementation | rule manager | implementation | 0 | 0 | 0 | 9 | 0 | 0 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-13 09:00 | 2015-06-13 18:00 | Shadyside Inn | Experiment | implementation | UI | implementation | 9 | 0 | 0 | 0 | 0 | 0 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-13 09:00 | 2015-06-13 18:00 | Shadyside Inn | Experiment | implementation | communication manager | implementation | 0 | 9 | 0 | 0 | 0 | 0 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-13 09:00 | 2015-06-13 18:00 | Shadyside Inn | Experiment | implementation | Arduino | implementation | 0 | 0 | 0 | 0 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-13 09:00 | 2015-06-13 18:00 | Shadyside Inn | Experiment | implementation | node manager | implementation | 0 | 0 | 9 | 0 | 0 | 0 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 9 | 9 | 9 | 9 | 9 | 9 | 54 |  |  | 9 | 9 | 9 | 9 | 9 | 9 | 54
2015-06-14 09:00 | 2015-06-14 18:00 | Shadyside Inn | Experiment | implementation | Arduino | implementation | 0 | 0 | 0 | 0 | 0 | 9 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-14 09:00 | 2015-06-14 18:00 | Shadyside Inn | Experiment | implementation | rule manager | implementation | 0 | 0 | 0 | 9 | 0 | 0 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-14 09:00 | 2015-06-14 18:00 | Shadyside Inn | Experiment | implementation | UI | implementation | 9 | 0 | 0 | 0 | 0 | 0 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-14 09:00 | 2015-06-14 18:00 | Shadyside Inn | Experiment | implementation | communication manager | implementation | 0 | 9 | 0 | 0 | 0 | 0 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-14 09:00 | 2015-06-14 18:00 | Shadyside Inn | Experiment | implementation | Arduino | implementation | 0 | 0 | 0 | 0 | 9 | 0 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-14 09:00 | 2015-06-14 18:00 | Shadyside Inn | Experiment | implementation | node manager | implementation | 0 | 0 | 9 | 0 | 0 | 0 | 9 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 9 | 9 | 9 | 9 | 9 | 9 | 54 |  |  | 9 | 9 | 9 | 9 | 9 | 9 | 54
2015-06-15 14:00 | 2015-06-15 21:00 | Shadyside Inn | Experiment | implementation | Arduino | implementation | 0 | 0 | 0 | 0 | 0 | 7 | 7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-15 14:00 | 2015-06-15 21:00 | Shadyside Inn | Experiment | implementation | rule manager | implementation | 0 | 0 | 0 | 7 | 0 | 0 | 7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-15 14:00 | 2015-06-15 21:00 | Shadyside Inn | Experiment | implementation | UI | implementation | 7 | 0 | 0 | 0 | 0 | 0 | 7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-15 14:00 | 2015-06-15 21:00 | Shadyside Inn | Experiment | implementation | communication manager | implementation | 0 | 7 | 0 | 0 | 0 | 0 | 7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-15 14:00 | 2015-06-15 21:00 | Shadyside Inn | Experiment | implementation | Arduino | implementation | 0 | 0 | 0 | 0 | 7 | 0 | 7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-15 14:00 | 2015-06-15 21:00 | Shadyside Inn | Experiment | implementation | node manager | implementation | 0 | 0 | 7 | 0 | 0 | 0 | 7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 7 | 7 | 7 | 7 | 7 | 7 | 42 |  |  | 7 | 7 | 7 | 7 | 7 | 7 | 42
2015-06-16 20:00 | 2015-06-16 23:00 | Shadyside Inn | meeting 10th Pittsburgh | Design | view | update view(dynamic,allocation) | 3 | 3 | 3 | 3 | 3 | 3 | 18 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 3 | 3 | 3 | 3 | 3 | 3 | 18 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 18
2015-06-17 12:30 | 2015-06-17 13:10 | CMU | meeting 4th with mentor | mentoring | review | review implementation | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 4 |  |  | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 0.66667 | 4
2017-06-17 14:00 | 2017-06-17 21:00 | Shadyside Inn | Experiment | implementation | integration | integration implementation | 0 | 7 | 7 | 7 | 7 | 7 | 35 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2017-06-17 14:00 | 2017-06-17 21:00 | Shadyside Inn | Experiment | implementation | UI | implementation | 7 | 0 | 0 | 0 | 0 | 0 | 7 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 7 | 7 | 7 | 7 | 7 | 7 | 42 |  |  | 7 | 7 | 7 | 7 | 7 | 7 | 42
2015-06-19 15:00 | 2015-06-19 17:00 | Shadyside Inn | meeting 11th Pittsburgh | Design | documentation | plan to make final document | 2 | 2 | 2 | 2 | 2 | 2 | 12 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-19 20:00 | 2015-06-19 23:00 | Shadyside Inn | module test | test | Arduino | implementation | 0 | 0 | 0 | 0 | 0 | 3 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-19 20:00 | 2015-06-19 23:00 | Shadyside Inn | module test | test | rule manager | implementation | 0 | 0 | 0 | 3 | 0 | 0 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-19 20:00 | 2015-06-19 23:00 | Shadyside Inn | module test | test | UI | implementation | 3 | 0 | 0 | 0 | 0 | 0 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-19 20:00 | 2015-06-19 23:00 | Shadyside Inn | module test | test | communication manager | implementation | 0 | 3 | 0 | 0 | 0 | 0 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-19 20:00 | 2015-06-19 23:00 | Shadyside Inn | module test | test | Arduino | implementation | 0 | 0 | 0 | 0 | 3 | 0 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-19 20:00 | 2015-06-19 23:00 | Shadyside Inn | module test | test | node manager | implementation | 0 | 0 | 3 | 0 | 0 | 0 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 5 | 5 | 5 | 5 | 5 | 5 | 30 |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 30
2015-06-20 14:00 | 2015-06-20 18:00 | Shadyside Inn | integration test | test | all integration test | implementation | 4 | 4 | 0 | 4 | 4 | 4 | 20 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2015-06-20 14:00 | 2015-06-20 18:00 | Shadyside Inn | documentation | documentation | documentation | make final document draft | 0 | 0 | 4 | 0 | 0 | 0 | 4 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 4 | 4 | 4 | 4 | 4 | 4 | 24 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 24
2115-06-21 19:00 | 2115-06-22 | Shadyside Inn | integration test | test | all integration test | implementation | 3 | 3 | 0 | 3 | 3 | 3 | 15 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2115-06-21 19:00 | 2115-06-22 | Shadyside Inn | documentation | documentation | documentation | make final document | 0 | 0 | 3 | 0 | 0 | 0 | 3 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 3 | 3 | 3 | 3 | 3 | 3 | 18 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 18
2115-06-22 20:00 | 2115-06-22 23:00 | Shadyside Inn | documentation | documentation | documentation | make final document | 3 | 3 | 3 | 3 | 3 | 3 | 18 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 3 | 3 | 3 | 3 | 3 | 3 | 18 |  |  | 3 | 3 | 3 | 3 | 3 | 3 | 18
2115-06-23 16:00 | 2115-06-24 | Shadyside Inn | integration test | test | all integration test | implementation | 8 | 8 | 0 | 0 | 8 | 0 | 24 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2115-06-23 16:00 | 2115-06-24 | Shadyside Inn | documentation | documentation | documentation | make final document | 0 | 0 | 8 | 8 | 0 | 8 | 24 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 8 | 8 | 8 | 8 | 8 | 8 | 48 |  |  | 8 | 8 | 8 | 8 | 8 | 8 | 48
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[13 empty] | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | total | 137.6667 | 129.6667 | 129.6667 | 136.6667 | 129.6667 | 129.6667 | 793

## WBS_old
Stage | Task | Description | Status | plan |  | actual |  | member
|  |  |  | Start Date | End date | Start Date | End date | JH Han | Y Kwon | DW Min | BH Jung | YG Jang | JW Hyun | total
Plan & analysis increment 1 | Project scope | Define project scope. So find out contexts of market, business, organization, technology. | close | 2015-05-07 | 2015-05-15 | 2015-05-07 | 2015-05-07
| Team Building | Confirm roles and responsibility of each members | close | 2015-05-07 | 2015-05-15 | 2015-05-07 | 2015-05-07
| Work Break Down | Tear down project work task | close | 2015-05-07 | 2015-05-15 | 2015-05-12 | 2015-05-12
| Overall Schedule | Set up a plan of schedule | close | 2015-05-07 | 2015-05-15 | 2015-05-12 | 2015-05-12
| requirement | Find out functional requirement | close | 2015-05-07 | 2015-05-15 | 2015-05-07 | 2015-05-12
| feasibility | Check spec. of Arduino and IDE | close | 2015-05-07 | 2015-05-15 | 2015-05-07 | 2015-05-14
| use case scenario | Make sample use-case scenarios | close | 2015-05-07 | 2015-05-15 | 2015-05-07 | 2015-05-12
| quality attribute | Find out quality attributes | close | 2015-05-07 | 2015-05-15 | 2015-05-14 | 2015-05-14
| constraint | Find out constraint | close | 2015-05-07 | 2015-05-15 | 2015-05-07 | 2015-05-12
| Risk analysis | Analyze risks of project | close | 2015-05-07 | 2015-05-15 | 2015-05-07 | 2015-05-12
analysis increment 2 | requirement | Refine functional requirement | open | 2015-06-08 | 2015-06-10 | - | -
| use case scenario | Refine use-case scenarios | open | 2015-06-08 | 2015-06-10 | - | -
| quality attribute constraint | Refine out quality attributes | open | 2015-06-08 | 2015-06-10 | - | -
| constraint | Refine constraint | open | 2015-06-08 | 2015-06-10 | - | -
Design increment 1 | use case description | Make use case description | open | 2015-05-15 | 2015-05-29 | - | -
| domain model | Make domain model | open | 2015-05-15 | 2015-05-29 | - | -
| sequence diagram | Find out sequences of system process and make diagram | open | 2015-05-15 | 2015-05-29 | - | -
| class diagram | Architect and design the system. | open | 2015-05-15 | 2015-05-29 | - | -
Design increment 2 | use case description | Improve use case description | open | 2015-06-11 | 2015-06-12 | - | -
| domain model | Improve domain model | open | 2015-06-11 | 2015-06-12 | - | -
| sequence diagram | Improve sequences of system process / diagram | open | 2015-06-11 | 2015-06-12 | - | -
| class diagram | Improve design | open | 2015-06-11 | 2015-06-12 | - | -
Implementation increment 1 | communication unit test | Implement each functions with testing units. | open | 2015-05-28 | 2015-06-07 | - | -
| logging unit test | Implement each functions with testing units. | open | 2015-05-28 | 2015-06-07 | - | -
| user command unit test | Implement each functions with testing units. | open | 2015-05-28 | 2015-06-07 | - | -
| rule unit test | Implement each functions with testing units. | open | 2015-05-28 | 2015-06-07 | - | -
| application unit test | Implement each functions with testing units. | open | 2015-05-28 | 2015-06-07 | - | -
| login unit test | Implement each functions with testing units. | open | 2015-05-28 | 2015-06-07 | - | -
| register node unit test | Implement each functions with testing units. | open | 2015-05-28 | 2015-06-07 | - | -
| setup unit test | Implement each functions with testing units. | open | 2015-05-28 | 2015-06-07 | - | -
| integration test | Implement each functions with testing units. | open | 2015-05-28 | 2015-06-07 | - | -
Implementation increment 2 | communication unit test | Implement each functions with testing units. | open | 2015-06-08 | 2015-06-25 | - | -
| logging unit test | Implement each functions with testing units. | open | 2015-06-08 | 2015-06-25 | - | -
| user command unit test | Implement each functions with testing units. | open | 2015-06-08 | 2015-06-25 | - | -
| rule unit test | Implement each functions with testing units. | open | 2015-06-08 | 2015-06-25 | - | -
| application unit test | Implement each functions with testing units. | open | 2015-06-08 | 2015-06-25 | - | -
| login unit test | Implement each functions with testing units. | open | 2015-06-08 | 2015-06-25 | - | -
| register node unit test | Implement each functions with testing units. | open | 2015-06-08 | 2015-06-25 | - | -
| setup unit test | Implement each functions with testing units. | open | 2015-06-08 | 2015-06-25 | - | -
| integration test | Implement each functions with testing units. | open | 2015-06-08 | 2015-06-25 | - | -
| system test | Implement each functions with testing units. | open | 2015-06-08 | 2015-06-25 | - | -